## Project Info
CSIS 2430 — Project Plan (Plan + Trace)
1) Project Information
Course / Term: CSIS 2430
Project: Project 3 (Team)
Team Name: Group 1
Start Date: 2026-03-27
Due Date: 2026-04-12
Checkpoint Date (Mid-Project): 2026-04-05
2) Team & Roles (assigned for this project)
Roles are assigned per project and rotate between projects.
Team Member | Role (Implementation / Verification / Communications) | Primary Responsibilities (1–2 bullets) | Availability / Notes
Pong Vodmongkol | Communications Lead (Inactive) | Assembles report/video; ensures run instructions; tracks deliverables; merges documentation.
Michael McCleary | Communications Lead (Inactive) | Assembles report/video; ensures run instructions; tracks deliverables; merges documentation.
Keanu Cruz | Verification Lead | Creates test plan; edge cases; validates outputs; documents verification evidence. | Mornings 6 – 9:30am & Weekends
Johnathan McElprang | Implementation Lead | Owns core algorithm implementation; integrates modules; maintains main branch health.
3) Repository & Access (Required for Projects 1–4)
Platform: GitHub
Repository URL: https://github.com/jmack02-ui/Programming_Project_3
Instructor invited as viewer by checkpoint?: YES Invited 3/28/2026
Repo Structure Requirement (summary): Inside README.md
Git Workflow
Commits are never made to made to the main branch. Work is committed in separate branches, then merged through PR into main.
Owners
Different parts of the repo have different 'owners'. Owners can merge their changes to their responsible files without review. If you change files that are owned by somebody else, the owner must review the PR first. Once PRs are reviewed and approved, the PR creator is responsible for merging their changes in. Branches are deleted after merge, unless they're being used intentionally for long-term changes.
Project2/src/* Owned by Implementation Lead.
Project2/test/* Owned by Validation Lead.
docs/* Owned by Communication Lead.

## Milestones
4) Milestones (Timeline)
Define 4–6 milestones. Each milestone has a definition of done. Status: NS / IP / D.
Milestone | Target Date | Owner | Definition of Done | Status (NS/IP/D) | Evidence Link / Pointer
Repo Set Up + Skeleton Running | 2026-03-29 | John | Repo created; README run steps; sample I/O runs. | D | e61faaf, PR#4
Core Implementation Complete | 2026-04-05 | John | All required features implemented; compiles/runs end-to-end. | IP | PR#4
Verification complete | 2026-04-05 | Keanu | Test suite covers edge cases; expected vs actual documented. | IP | PR#5
Report/Video Draft Complete | 2026-04-11 | Michael/Pong | Draft report sections complete; video outline + script notes.
Final Integration + Submission | 2026-04-12 | Michael/Pong | All deliverables finalized; tags release; submission package ready.

## Tasks
5) Task Backlog (Assignments + Status)
Keep this concise (8–15 tasks). For each Done task, include an evidence pointer.
ID | Task | Owner | Due Date | Status (NS/IP/D) | Evidence Link / Pointer | Notes / Dependencies
1 | Design Basic Code Layout, Build Boiler Plate | John | 2026-03-29 | D | aa167c2, a8ff682
2 | Fill Out Implementations For All Classes | John | 2026-04-05 | D | PR#4
3 | Finish Final Touch Ups For All Classes, Comments. | John | 2026-04-11 | IP
4 | Write Up Relevant Sections For Final Submission Paper | John | 2026-04-11
5 | Build List For All Test Types | Keanu | 2026-03-29 | D | a8c3ab2
6 | Impliment All Tests | Keanu | 2026-04-05 | D | PR#5
7 | Ensure All Classes Pass Test | Keanu | 2026-04-11 | IP | Issue#3
8 | Write Up Relevant Sections For Final Submission Paper | Keanu | 2026-04-11
9 | Ensure Basic Docs Are Present | Michael/Pong | 2026-03-29 | D | 0c8127b, cb6381e | Done by Keanu
10 | Ensure Correct Run Instruction Exist | Michael/Pong | 2026-04-05 | D | e61faaf | Done by Keanu
11 | Compile Project Checkpoint + Submit | Michael/Pong | 2026-04-05 | D | Submitted 4/5/2026 | Done by Keanu
12 | Compile Final Submission + Submit | Michael/Pong | 2026-04-12

## Verification Plan
Part I - Tests for Greedy Strategies
Standard Expected Operation
Highest Rating Does Not Exceed Bounds
Lightest Weight Does Not Exceed Bounds
Does Not Divide by Zero
Empty Experiment List
All Experiments Too Heavy
High Rating High Weight
Low Weight Low Rating
Same Weight Same Rating Multiple Items
Same Ratio Multiple Items
Sort Order Consistency
Part II - Tests for Brute Force Strategies
Standard Expected Operation
Less than 3 Subsets
Optimal Case Check
Subset Count Validation
Multiple Subsets Same Rating
Subsets Within Weight Bounds
No Valid Subsets
Order Independence
Part III - Comparison Output
Output Works As Intended
Correct Totals
Correct Experiment Outputs
Greedy Fails Vs Brute Force
Solver Immutable
Part IV - Dynamic Programming (Optional)

## Risks
7) Risks / Blockers
Risk / Blocker | Impact | Mitigation Plan | Owner | Status
KnapsackSolver Deep Copy | Low | Issue#3 needs to be corrected | John | IP

## Updates
8) Update Log (Required: at least 2 per project)
Date | Summary of Update (what changed / what completed) | Blockers / Resolutions | Link(s)
2026-04-04 | Code Implemented |  | PR#4
2026-04-04 | Tests Implemented |  | PR#5
2026-04-05 | Docs Present and Updated for Checkpoint |  | a47ba88